## Cover
ABC Company
PROJECT DETAIL PLAN
| Code | SP24SAP04
| Version | 1.0
| Effective Date | 2024-05-27

## Project Timeline
PROJECT TIMELINE
[5 empty] | 2024-01-01 |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01 |  |  |  | 2024-05-01 |  |  |  | Status | Notes
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Project Plan |  | Rheem,FPT | 1 week | [20 empty] | Done
2 | Knowledge Transfer |  | Rheem,FPT | 1 week | [20 empty] | Done | bar: 2024-01-01 1
3 | Process Adoption |  |  | 2 weeks | [20 empty] | Done
3.1 | Project Kick-off | Offshore | FPT | [21 empty] | Done | bar: 2024-01-01 2
3.2 | Define problem statement (Customer Definiton, Current Processes and Limitations) | Onsite | Rheem,FPT | [21 empty] | Done | bar: 2024-01-01 2
3.3 | Define Requirement Analysis (Customer Requirements, SAP Solution) | Onsite | Rheem,FPT | [21 empty] | Done | bar: 2024-01-01 2 to 2024-01-01 4
3.4 | Write a preliminary report on topic thesis "Process of integrating Bank Statement, LockBox" (based on the suggested Mentor template) | bar: 2024-01-01 2 to 2024-01-01 4
4 | Processes Finalization |  |  | 1 week | bar: 2024-01-01 2 to 2024-01-01 4
4.1 | Draw Business Process for Outgoing Bank Integration | bar: 2024-01-01 2 to 2024-01-01 4
4.2 | Draw Business Process for Incoming Bank Integration | bar: 2024-01-01 2 to 2024-01-01 4
4.3 | Draw Business Process for Import Bank Statement | bar: 2024-01-01 2 to 2024-01-01 4
4.4 | Draw business process for Incoming Payment with Electronic Bank Statement | bar: 2024-01-01 2 to 2024-01-01 4
4.5 | Draw business process for LockBox Integration | bar: 2024-01-01 2 to 2024-01-01 4
5 | Project Scopes |  |  | 1 week | bar: 2024-01-01 2 to 2024-01-01 4
2024-01-05 | Define project scope & limitations | bar: 2024-01-01 2 to 2024-01-01 4
| Finish Report 1 | [23 empty] | Done
6 | Define System Infrastructure |  |  | 1 week | [20 empty] | Done
2024-01-06 | Define System Landscape | [23 empty] | Done | bar: 2024-02-01 3 to 2024-03-01 1
2024-02-06 | Define Transport Request Management | [23 empty] | Done | bar: 2024-02-01 4 to 2024-03-01 2
7 | Realization |  |  | 1 week | [20 empty] | Done | bar: 2024-03-01 4
7.1 | SAP Configuration |  | FPT | [21 empty] | Done | bar: 2024-02-01 3 to 2024-03-01 4
| Configuration |  | Rheem | bar: 2024-04-01 3 to 2024-04-01 4
| Unit Test/Test cases |  | FPT | [21 empty] | Done
| Configuration Notes | [23 empty] | Done | bar: 2024-03-01 1
| Master Data Configuration | [23 empty] | Done | bar: 2024-02-01 3 to 2024-02-01 4
| Electronic Bank Statement Configuration | [23 empty] | Done | bar: 2024-03-01 1 to 2024-03-01 3
| LockBox Configuration |  | FPT | [21 empty] | Done | bar: 2024-03-01 3 to 2024-03-01 4
Finish Report 2 | bar: 2024-03-01 3 to 2024-03-01 4
8 | Coding |  | FPT | 3 weeks | [20 empty] | Done | bar: 2024-03-01 3 to 2024-03-01 4
8.1 | User Exit for Processing Bank Statement |  | FPT | [21 empty] | Done | bar: 2024-03-01 1 to 2024-04-01 1
| Enhance Exit Function in DMEE File | [23 empty] | Done | bar: 2024-03-01 1
Smartforms | bar: 2024-03-01 1 to 2024-03-01 4
Set Up Batch for Automatic Clearing (F.13) | bar: 2024-03-01 4 to 2024-04-01 1
Finish Configuration NoteBook | bar: 2024-04-01 1
| Authorization/ Roles Configuration | [23 empty] | Done
| Finish Report 3 | [23 empty] | Done | bar: 2024-03-01 4
9 | Final Preparation |  | FPT | [21 empty] | Done | bar: 2024-03-01 4 to 2024-04-01 1
2024-01-09 | Define Test Cases | [23 empty] | Done | bar: 2024-04-01 2 to 2024-04-01 3
| Define Test Reports | [23 empty] | Done | bar: 2024-04-01 4 to 2024-05-01 1
Define Test Environment
10 | Go-live |  | FPT | bar: 2024-04-01 4 to 2024-05-01 2
11 | Finish Report 4 | [23 empty] | Done

## Project Details Plan
Project ID: SP24SAP04
Customer Name: ABC Limited Company
Updated By: …
No. |  | Location | Parties | FSOFT PIC | ABC PIC | Planned Duration (Hrs) | Planned Date |  | Planned Time |  | Actual Duration | Actual Date |  | Actual Time |  | Status | Notes
[7 empty] | From | To | VNT UTC +7:00 | EDT UTC -5:00 |  | From | To | VNT UTC +7:00 | EDT UTC -5:00
1 | Project Plan |  | Rheem,FPT |  |  | 1 week | [9 empty] | Done
2 | Knowledge Transfer |  | Rheem,FPT |  |  | 2 week | [9 empty] | Done
3 | Process Adoption | Online |  | HuyNM | Taylor | 2 | 2024-01-04 | 2024-01-31 | 9:30-11:30 | 12:30-14:30 | 2 | 2024-01-04 | 2024-01-31 |  |  | Done
3.1 | Project Kick-off | Online |  | CuongVM | Justin | 2 | 2024-01-04 | 2024-01-09 | 10:00-12:00 | 13:00-15:00 | 1 | 2024-01-04 | 2024-01-09 |  |  | Done
3.2 | Define problem statement (Customer Definiton, Current Processes and Limitations) |  |  | HuyNM | Taylor | 5 weeks | 2024-01-09 | 2024-01-15 | [7 empty] | Done
3.3 | Define Requirement Analysis (Customer Requirements, SAP Solution) |  | Rheem,FPT | HuyNM | Taylor | 1H | 2024-01-15 | 2024-01-20 | 12:30-13:30 | 15:30-16:30 | [5 empty] | Done
3.4 | Write a preliminary report on topic thesis "Process of integrating Bank Statement, LockBox" (based on the suggested Mentor template) | Offshore | FPT | HuyNM | Taylor | 1 week | 2024-01-20 | 2024-01-25
4 | Processes Finalization | Offshore | FPT |  |  | 24 | 2024-01-25 | 2024-02-12 |  |  |  | 2024-01-25 | 2024-02-12 |  |  | Done
4.1 | Draw Business Process for Outgoing Bank Integration | Online | Rheem,FPT | NamVT | Jennifer | 2 weeks | 2024-01-25 | 2024-02-05 | [7 empty] | Done
4.2 | Draw Business Process for Incoming Bank Integration | Online | Rheem,FPT | CuongVM | Justin |  | 2024-02-05 | 2024-02-08
4.3 | Draw Business Process for Import Bank Statement | Online | Rheem,FPT | ChienNM | Jennifer | 4 | 2024-02-05 | 2024-02-08 | 13:00-17:00 |  | 3 | 2024-02-05 | 2024-02-08 |  |  | Done
4.4 | Draw business process for Incoming Payment with Electronic Bank Statement | Online | Rheem,FPT | ChienNM | Jennifer | 2 | 2024-02-08 | 2024-02-10 | 8:00-12:00 |  | 3 | 2024-02-08 | 2024-02-10 |  |  | Done
4.5 | Draw business process for LockBox Integration | Online | Rheem,FPT | NamVT | Jennifer | 2 | 2024-02-10 | 2024-02-12 | 10:00-12:00 |  |  | 2024-02-10 | 2024-02-12 |  |  | Done
5 | Project Scopes | Onsite | Rheem,FPT |  |  | 1 week | 2024-02-15 | 2024-02-18
2024-01-05 | Define project scope & limitations | Offshore | FPT | ChienNM | Jennifer | 2 weeks | 2024-02-15 | 2024-02-18 | [7 empty] | Done
| Finish Report 1 | Offshore | FPT | HuyNM | Taylor
6 | Define System Infrastructure | Offshore | FPT | ChienNM | Jennifer | 8 | 2024-02-18 | 2024-02-20 |  |  |  | 2024-02-18 | 2024-02-20 |  |  | Done
2024-01-06 | Define System Landscape | Offshore | FPT | ChienNM | Jennifer | 8 | 2024-02-18 | 2024-02-19 |  |  |  | 2024-02-18 | 2024-02-19 |  |  | Done
2024-02-06 | Define Transport Request Management |  |  | HuyNM | Taylor |  | 2024-02-19 | 2024-02-20
7 | Realization | Offshore | FPT |  |  | 8 | 2024-02-21 | 2024-03-05 |  |  |  | 2024-02-21 |  |  |  | Done
7.1 | SAP Configuration | Online | Rheem,FPT
| Configuration | Online | Rheem,FPT | ChienNM | Jennifer | 1.5 | 2024-02-21 | 2024-02-23 | 10:00 - 11:30 | 13:00 - 14:30 |  | 2024-02-21 | 2024-02-23 | 10:00 - 11:30 | 13:00 - 14:30 | Done
| Unit Test/Test cases | Onsite | Rheem | ChienNM | Jennifer
| Configuration Notes | Onsite | Rheem | HuyNM | Taylor |  | 2024-02-23 | 2024-02-25 |  |  |  | 2024-02-23 | 2024-02-25 |  |  | Done
| Master Data Configuration | Onsite | Rheem | ChienNM | Jennifer |  | 2024-02-25 | 2024-02-27 |  |  |  | 2024-02-25 | 2024-02-27 |  |  | Done
| Electronic Bank Statement Configuration | Onsite | Rheem,FPT | ChienNM | Jennifer | 2 weeks | 2024-03-01 | 2024-03-05
| DMEE Configuration |  |  | ChienNM | Jennifer
| LockBox Configuration | Offshore | FPT | ChienNM | Jennifer |  | 2024-03-01 | 2024-03-05 |  |  |  | 2024-03-01 | 2024-03-05 |  |  | Done
| Finish Report 2 |  | Rheem | HuyNM | Taylor |  | 2024-03-01 | 2024-03-05 |  |  |  | 2024-03-01 | 2024-03-05 |  |  | Done
8 | Coding | [5 empty] | 2024-03-05 | 2024-05-30
8.1 | User Exit for Processing Bank Statement |  |  | CuongVM | Justin |  | 2024-03-05 | 2024-05-20 |  |  |  | 2024-03-05 | 2024-05-20 |  |  | Done
| Enhance Exit Function in DMEE File |  |  | HuyNM | Taylor |  | 2024-03-05 | 2024-03-20
| Smartforms |  |  | NamVT | Jennifer |  | 2024-03-20 | 2024-04-10 |  |  |  | 2024-03-20 | 2024-04-10 |  |  | Done
| Set Up Batch for Automatic Clearing (F.13) |  |  | NamVT | Jennifer | 6 weeks | 2024-04-10 | 2024-04-15 | [7 empty] | Done
| Deploy Tcode of Forms to Fiori |  |  | NamVT | Jennifer
| Finish Configuration NoteBook | Offshore | FPT | CuongVM | Justin | 3W | 2024-04-15 | 2024-04-25 | [7 empty] | Done
| Authorization/ Roles Configuration |  |  | HuyNM | Taylor | 2W | 2024-04-25 | 2024-04-30 |  |  |  | 2024-04-25 | 2024-04-30 |  |  | Done
| Finish Report 3 |  |  | HuyNM | Taylor |  | 2024-05-01 | 2024-05-10 |  |  |  | 2024-05-01 | 2024-05-10 |  |  | Done
9 | Final Preparation |  |  |  |  | 1W | 2024-05-10 | 2021-05-31 |  |  |  | 2024-05-10
2024-01-09 | Define Test Cases |  |  | ChienNM | Jennifer |  | 2024-05-10 | 2024-05-21 |  |  |  | 2024-05-10 | 2024-05-21 |  |  | Done
| Define Test Reports |  |  | ChienNM | Jennifer | 1W | 2024-05-21 | 2024-05-30
| Define Test Environment |  |  | ChienNM | Jennifer |  | 2024-05-21 | 2024-05-30 |  |  |  | 2024-05-21 | 2024-05-30 |  |  | Done
10 | Go-live | Offshore | FPT | CuongVM | Justin | 2W | 2024-05-21 | 2024-05-30 | [7 empty] | Done
11 | Finish Report 4 |  | FPT | HuyNM | Taylor |  | 2024-05-21 | 2024-05-30 |  |  |  | 2024-05-21 | 2024-05-30 |  |  | Done